NEXARA

Integrated Management System

BCP Exercise & Testing Procedure

ISO 22301:2019 cl.8.5

| Document Number: | FEM-PRO-007 |
| --- | --- |
| Version: | 1.0 |
| Date: | [DD/MM/YYYY] |
| Owner: | [Business Continuity Manager] |
| Approved By: | [Managing Director] |
| Classification: | Confidential |

Revision History

| Version | Date | Description | Author | Approved By |
| --- | --- | --- | --- | --- |
| 1.0 | [DD/MM/YYYY] | Initial Issue | [Author Name] | [Approver Name] |

# 1. Purpose

This procedure defines the programme for exercising and testing Business Continuity Plans in accordance with ISO 22301:2019 Clause 8.5.

# 2. Exercise Programme

Minimum frequency: annually. Recommended 3-year cycle:

Year 1: Tabletop exercise — discussion-based scenario
Year 2: Functional exercise — test specific teams/functions
Year 3: Full-scale exercise — live activation with all resources

Additionally, single-procedure drills (IT failover, communications cascade, alternative site setup) may be conducted at any time.

# 3. Exercise Types

## 3.1 Tabletop

Discussion-based exercise where the Crisis Team walks through a scenario. No physical movement of resources. Duration: typically 2-4 hours. Suitable for validating plans, roles, decision-making processes.

## 3.2 Functional

Tests specific functions or teams in near-real-time. May involve IT failover, communications cascade, or team mobilisation. Duration: typically half to full day.

## 3.3 Full-Scale

Live exercise involving all resources, teams, and (where possible) external agencies. Simulates a real disruption as closely as possible. Duration: typically 1-2 days. Requires significant planning (minimum 3 months lead time).

# 4. Planning Requirements

- Define clear, measurable objectives

- Select appropriate scenario (realistic, challenging but achievable)

- Identify participants and observers

- Brief all participants on exercise rules and safety

- Prepare injects (scenario developments)

- Arrange observers and evaluators

- Prepare evaluation forms

- Notify senior management and external parties if affected

# 5. Observer Roles

Observers shall be appointed to watch and evaluate the exercise without intervening. They shall record: decisions made and their timeliness, communications effectiveness, plan adherence, resource utilisation, any deviations from the plan.

# 6. Finding Categorisation

Exercise findings shall be categorised as:

Strength: Procedure or action that worked well
Weakness: Area that needs improvement but did not prevent recovery
Failure: Critical gap that would prevent or significantly delay recovery

# 7. Action Tracking

All weaknesses and failures shall generate actions, tracked using the FEM-FRM-007 BCP Exercise Report Template. Actions must have: description, owner, target date. Actions shall be tracked to completion before the next exercise.

# 8. Lessons Learned

Following each exercise, the BCP shall be updated to reflect lessons learned. Updates shall be version-controlled. All participants shall receive a summary of findings and actions.

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Prepared by | [Name] |  | [DD/MM/YYYY] |
| Approved by | [Managing Director] |  | [DD/MM/YYYY] |